## Task List
Task ID | Owner | Milestone | Title | Weight (0-100] | Start Date and Time | Completed Date and Time | URL | Details
1 | Melih Berk Sönmez |  | Create Resources (Lifestyle, Goods, Population) | 10 | 2026-04-30 20:27 | 2026-04-30 20:51 | Added Resource, Lifestyle, Population, and Goods · iyiinsan5555/objectville-ii-se116@2b5f079 | Based on our project design I have implemented the prelimenary classes Resource, Lifestyle, Population, and Goods. They were planned to be used as a data type.
2 | Melih Berk Sönmez |  | Create ServiceProvider class | 10 | 2026-05-05 19:47 | 2026-05-05 19:56 | Add ServiceProvider · iyiinsan5555/objectville-ii-se116@ad4109b | Created ServiceProvider according to our project design. ServiceProvider is the abstract classes that will be used by School, PoliceStation, and Hospital.
3 | Melih Berk Sönmez |  | Add Hospital | 10 | 2026-05-05 19:47 | 2026-05-05 19:59 | Add Hospital · iyiinsan5555/objectville-ii-se116@93a8d3c | Hospital is subclass of the ServiceProvider. Its distribution logic is not done.
4 | Melih Berk Sönmez |  | Add PoliceStation | 10 | 2026-05-05 19:47 | 2026-05-05 20:01 | Add PoliceStation · iyiinsan5555/objectville-ii-se116@3245c0f | PoliceStation is subclass of the ServiceProvider. It will provide Security but its distribution logic will be implemented later.
5 | Melih Berk Sönmez |  | Add School | 10 | 2026-05-05 19:47 | 2026-05-05 20:02 | Add School · iyiinsan5555/objectville-ii-se116@8ddd233 | Subclass of the ServiceProvider. It will provide Education.
6 | Melih Berk Sönmez |  | Fix ServiceProvider&Subclasses | 10 | 2026-05-09 13:20 | 2026-05-09 13:29 | Edit ServiceProvider & Subclasses · iyiinsan5555/objectville-ii-se116@ee83d45 | We have reviewed and altered our project design. Based on the new design, I have made some changes.
7 | Mert Akalın |  | Create ServiceDistributor | 50 | 2026-05-10 16:40 | 2026-05-11 17:52 | Create ServiceDistributor.java · iyiinsan5555/objectville-ii-se116@93e3095 | Created ServiceDistributor class. It oversees all the Cells and handles service distributon logic.
8 | Umut Utkan Göbelek |  | Create UtilityDistributor | 90 | 2026-05-07 | 2026-05-19 | Finished UtilityDistributor | Created UtilityDistributor who distributes all utilities by iterating over cells and using a Breadth First Search algorithm.
9 | Umut Utkan Göbelek |  | Add Cell | 20 | 2026-05-04 | 2026-05-05 | Created Cell | Cell class is the superclass of all entities in the program
10 | Umut Utkan Göbelek |  | Add Road | 10 | 2026-05-04 | 2026-05-05 | Add Road,Empty,Transferrable | Road cells just transfers utilities without using them
11 | Umut Utkan Göbelek |  | Create Point | 25 | 2026-05-04 | 2026-05-05 | Created Point | Point class lets us create a grid system and put all cells in a location
12 | Umut Utkan Göbelek |  | Add Empty | 10 | 2026-05-04 | 2026-05-05 | Add Road,Empty,Transferable | Empty cells prevents the Utility distributor from accessing the cells behind it
13 | Umut Utkan Göbelek |  | Create Transferable | 10 | 2026-05-04 | 2026-05-05 | Add Road,Empty,Transferable | the cells that implement this interface let the Utility Distributor go through them while in the process of BFS
14 | Umut Utkan Göbelek |  | Add package system | 10 | 2026-06-01 | 2026-06-01 | Package System | this is to make our code tidier
15 | Melih Berk Sönmez |  | Add MapReader | 40 | 2026-05-10 07:36 | 2026-05-10 09:19 | Add MapReader & ExampleMap.txt · iyiinsan5555/objectville-ii-se116@2a389cd | The MapReader class uses a method readMap(Path mapPath) which returns an array list of cells.
16 | Melih Berk Sönmez |  | Add GridManager | 35 | 2026-05-11 08:02 | 2026-05-11 09:33 | Add GridManager · iyiinsan5555/objectville-ii-se116@b513897 | The grid manager gets an array list of cells and provides some utilities. (Has both static and non-static util methods) (Later we altered it)
17 | Melih Berk Sönmez |  | Add SimulationRunner | 40 | 2026-05-13 17:54 | 2026-05-13 18:34 | Fix GridManager & Add SimulationRunner · iyiinsan5555/objectville-ii-se116@d578f69 | The simulation runner will be the main component to run the game. In main method we will create and run it.
18 | Gökçe Ünsal |  | Create Zone Class | 30 | 09.05.2026 17.30 | 09.05.2026 18.03 | Add Zone | Created the base structure for all zones, including core attributes, encapsulation, getM() utility calculation logic, and abstract methods required for Step 4 updates.
19 | Gökçe Ünsal |  | Implement Housing | 25 | 09.05.2026 18.15 | 16.05.2026 11.11 | Add Housing | Coded the population generation logic, lifestyle integration, the gradual level drop mechanism (gradual fall), and specific resetData() operations for unique resources.
20 | Gökçe Ünsal |  | Implement Industrial | 25 | 16.05.2026 11.20 | 16.05.2026 11.55 | Add Industrial | Overrode the getM() method to restrict utility needs to only Electricity and Water, implemented population consumption and goods generation based on the output table, and added gradual fall logic.
21 | Gökçe Ünsal |  | Implement Commercial | 25 | 16.05.2026 12.12 | 16.05.2026 12.34 | Add Comercial | Wrote the output formula using Math.min(population, goods). Tracked population and goods variables. Added the 3 utility needs and gradual level drop rules.
22 | Gökçe Ünsal |  | Add ResourceDistributor | 60 | 16.05.2026 16.12 | 16.05.2026 17.58 | Add ResourceDistributor | Wrote the distribute (Step 3) and accumulate (Step 5) methods. Counted the zones to divide resources equally. Handled the integer division and city-wide pools.
23 | Gökçe Ünsal |  | Final Refactoring & Bug Fixes | 10 | 01.06.2026 12.00 | 01.06.2026 13.09 | Fixes & Updates | Fixed zero-division in ResourceDistributor, prevented negative utility values, and added utility checking methods to all zones.
24 | Mert Akalın |  | Add PowerPlant | 10 | 2026-05-10 | 2026-05-10 | Added PowerPlant | PowerPlant is subclass of the UtilityProvider. It contains electricity resource
25 | Mert Akalın |  | Add WaterPumpingStation | 10 | 2026-05-10 | 2026-05-10 | Added WaterPumpingStation | WaterPumpingStation is subclass of the UtilityProvider. It contains water resource
26 | Mert Akalın |  | Add InternetHub | 10 | 2026-05-10 | 2026-05-10 | Added InternetHub | InternetHubis subclass of the UtilityProvider. It contains Internet resource
27 | Mert Akalın |  | Add UtilityProvider | 35 | 2026-05-10 | 2026-05-10 | Added UtilityProvider | Parent class for utilities serves useful methods
28 | Mert Akalın |  | Add print level changes | 25 | 2026-05-30 | 2026-05-31 | Print Levels Print Levels Print Levels | Prints a detailed line when Housing, Industrial or Commercial commercial levels up or down. With coordinates.
29 | Mert Akalın |  | Add log produced output | 25 | 2026-05-30 | 2026-05-31 | Print Output Print Output Print Output | Prints a detailed line when Housing, Industrial or Commercial generates an output. With coordinates
30 | Mert Akalın |  | Print services received by zones | 5 | 2026-05-30 | 2026-05-31 | Print services | Prints received services by a zone measured with radius of a service provider.
31 | Mert Akalın |  | Minor fixes | 5 | 2026-06-01 | 2026-06-01 | Edit print logic | Made level up/down and received services print statements less redundant

## Developer List
Developer | Number of Tasks | Total Weight | Score | Team Average
Melih Berk Sönmez | 9 | 175 | 100 | 175
Umut Utkan Göbelek | 7 | 175 | 100
Gökçe Ünsal | 6 | 175 | 100
Mert Akalın | 9 | 175 | 100
0
0
0
0
0
0